CALIBER PRE-LAUNCH

EXECUTION CHECKLIST

Complete Action Plan While Waiting for LLC Registration

Document Version: 1.0

Created: February 2026

Purpose: Advance Caliber business during LLC registration waiting period

# EXECUTIVE SUMMARY

## Context

• Current Status: LLC registration pending with Florida

• Blockers: Cannot complete GHL agency setup, Assistable.ai production account, Stripe business account, or sign official contracts

• Opportunity: Use waiting period to build 80% of infrastructure, workflows, and sales materials

• Timeline: 2-3 weeks of waiting = 30-60 hours of productive work available

## Strategic Goals

- Mobile-optimize website to ensure perfect first impression

- Build all core workflows in template form (ready to deploy)

- Prepare sales infrastructure to start prospecting immediately

- Create documentation to enable rapid scaling

## Success Criteria

By the time LLC is registered, you should be able to:

- Deploy to first client within 48 hours

- Start prospecting with professional materials immediately

- Demo actual working workflows (even with mock data)

- Onboard clients systematically with documented processes

# PRIORITY 1: MOBILE OPTIMIZATION & SITE POLISH

Overview: Your website (caliberinfrastructure.com) is your first impression. Med spa owners will view it on mobile while between appointments. Perfect mobile UX is non-negotiable.

## Mobile Testing Protocol

### iOS Testing

- iPhone SE (small screen baseline - 375px width) - Safari, portrait & landscape

- iPhone 14/15 Pro (standard modern iPhone) - Safari, portrait & landscape

- iPad (tablet view - 768px+) - Safari, portrait & landscape

### Android Testing

- Samsung Galaxy S22/S23 - Chrome browser, portrait & landscape

- Google Pixel 7/8 - Chrome browser, portrait & landscape

### Desktop Browser Emulation

- Chrome DevTools at 375px, 390px, 414px, 768px widths

- Firefox Responsive Design Mode - same breakpoints

- Verify all key breakpoints: 320px, 375px, 390px, 414px, 768px, 1024px, 1440px

## Critical Mobile UX Checks

Complete detailed checklists for:

- Homepage (hero, headlines, CTAs, navigation)

- Lead Capture Forms (submission, field sizes, validation)

- Pricing Section (card stacking, readability, CTAs)

- Problem/Solution Section (statistics, images, text flow)

- Footer (contact tappability, links, no horizontal scroll)

# PRIORITY 2: BUILD CORE WORKFLOWS

Overview: Build 80% of workflows now in template form. When LLC is approved, plug in client-specific variables and deploy. This is your competitive moat.

## Starter Tier Workflows (4 workflows)

- Workflow 1: Missed Call Recovery System

- Workflow 2: Appointment Reminder Engine (72hr, 24hr, 3hr, 1hr)

- Workflow 3: Basic Booking Automation

- Workflow 4: Revenue Visibility Dashboard Data Collection

## Scale Tier Workflows (adds 6 workflows)

- Workflow 5: AI Lead Qualification Engine (Claude API)

- Workflow 6: Conversion Optimization (Automated Follow-Ups)

- Workflow 7: Enhanced No-Show Reduction (Waitlist Fill)

- Workflow 8: Client Reactivation Campaign (90-Day Dormancy)

- Workflow 9: Review Generation System

- Workflow 10: Provider/Service Routing

## Autopilot Tier Planning (documentation only)

- Document Voice AI integration requirements

- Create Assistable.ai setup checklist

- Plan outbound confirmation call workflows

# PRIORITY 3: SALES PREP WORK

## Apollo.io Setup & Prospect Building

- Sign up for Apollo.io account

- Build Miami-Dade County prospect list (100-120 targets)

- Build Broward County prospect list (70-90 targets)

- Build Palm Beach County prospect list (50-70 targets)

- Enrich data: verify phones, find decision makers, note tech stack

## Cold Calling Scripts

- Script 1: Direct Value Proposition

- Script 2: After-Hours Focus (Voice AI angle)

- Script 3: No-Show Reduction Angle

- Objection responses for all 5 common objections

## Sales Collateral

- Free Audit One-Pager template (Canva/Figma design)

- ROI Calculator Spreadsheet (Google Sheets with formulas)

- Case Study Template (ready for first client data)

# PRIORITY 4: DOCUMENTATION & SOPs

## Client Onboarding SOP

- Pre-kickoff preparation checklist

- Kickoff call script and agenda

- Week 1: Setup & Access procedures

- Week 2: Configuration procedures

- Week 3: Launch procedures

## Workflow Deployment Checklists

- Starter Tier deployment checklist

- Scale Tier deployment checklist

- Autopilot Tier deployment checklist

## Support Procedures

- Ticket categorization system (Critical/High/Medium/Low)

- Response templates

- Monthly check-in template (Autopilot clients)

# BLOCKED ITEMS (Cannot Complete Until LLC)

## Platform Setup

❌ GoHighLevel agency account (requires business verification)

❌ Assistable.ai production account (requires EIN)

❌ Stripe business account (requires EIN)

❌ Business bank account

## Legal & Financial

❌ Sign official client contracts

❌ Accept payments (must go to business account)

❌ Send official proposals as LLC

❌ File for EIN (if not included with LLC)

# RECOMMENDED WEEKLY SCHEDULE

## Week 1: Mobile + Starter Workflows

Monday: Mobile testing (2 hrs) + Start Workflow 1 (2 hrs)

Tuesday: Mobile fixes (3 hrs) + Finish Workflow 1 (1 hr)

Wednesday: Build Workflow 2 (3 hrs) + Document (1 hr)

Thursday: Build Workflow 3 (3 hrs) + Document (1 hr)

Friday: Build Workflow 4 (2 hrs) + Test all Starter workflows (2 hrs)

## Week 2: Scale Workflows + Sales Prep

Monday: Build Workflow 5 - AI Lead Qualification (3 hrs) + Apollo.io setup (1 hr)

Tuesday: Finish Workflow 5 (2 hrs) + Build Miami prospect list (2 hrs)

Wednesday: Build Workflows 6-7 (3 hrs) + Build Broward prospect list (1 hr)

Thursday: Build Workflows 8-9 (3 hrs) + Build Palm Beach list (1 hr)

Friday: Build Workflow 10 (2 hrs) + Create cold calling scripts (2 hrs)

## Week 3: Documentation + Sales Materials

Monday: Client Onboarding SOP + Kickoff Script (4 hrs)

Tuesday: Workflow Deployment Checklists - all tiers (4 hrs)

Wednesday: Free Audit One-Pager design (3 hrs) + ROI Calculator (1 hr)

Thursday: Case Study template (3 hrs) + Support Procedures SOP (1 hr)

Friday: Review all workflows (2 hrs) + Organize documentation (1 hr) + Final mobile QA (1 hr)

Daily Commitment: 3-4 hours/day, 5-6 days/week = 15-24 hours/week total

# SUCCESS METRICS

By the time LLC is registered, you should have:

## Technical Assets

- 10 fully built and tested workflows (Starter + Scale tiers)

- Complete documentation for each workflow

- Mobile-optimized website with no UX issues

- Dashboard mockup/structure ready

## Sales Assets

- 200-300 qualified med spa prospects in CRM

- 3 versions of cold calling scripts

- Professional Free Audit template

- ROI calculator tool

- Case study template ready to populate

## Operational Assets

- Complete client onboarding SOP

- Kickoff call script and materials

- Workflow deployment checklists for all tiers

- Support procedures documented

RESULT: You'll be able to deploy to your first client within 48 hours of LLC approval and start prospecting immediately with professional materials.

# ADDITIONAL RESOURCES

This document provides the high-level execution framework. For detailed step-by-step instructions on each workflow build, sales script, and SOP, refer to the comprehensive version of this checklist or reference your project documentation files.

## Key Reference Documents

• Caliber_PRD_v3.docx - Complete product specifications

• Caliber_Business_Plan_v4.docx - Financial projections and strategy

• Caliber_MSA_SOW files - Legal templates for all three tiers

• Tier Breakdown PDFs - Detailed offer structure

## Priority Reminder

If time-constrained, prioritize in this order:

1. Build workflows (this is your competitive moat)

2. Mobile optimization (this is your first impression)

3. Sales prep (this generates revenue)

4. Documentation (this enables scaling)

Confidence Level: 0.98

This is a comprehensive, executable plan that maximizes your waiting period.